

**Town of Eston 2020 Strategic Priorities**

**Update**

*As of February 2021*

**Overarching Principles**

Decisions and projects will be approached with the following themes in mind:

|  |  |  |  |
| --- | --- | --- | --- |
| **Continuous Improvement** | **Customer Service** | **Planning** | **Communication** |
| Activities will be approached with a goal of achieving excellence and being better at what we do and how we do it every day. | We will approach changes with improvement to and enhancement of the end user experience in mind. | We will undergo sound planning processes that will assist in preparing us for the future and maintaining a sustainable community. | We will strive to enhance communication and connectedness internally, externally and with key partners and stakeholders. |

**Overarching Areas of Focus**

Key projects and activities in 2020 will be based on the following four areas of focus or ‘pillars’:

|  |  |  |  |
| --- | --- | --- | --- |
| **Planning**  | **Capital and Infrastructure** | **Serving the Community, Programming and Events** | **Governance and Policy** |

**Planning**

1. Initiate the creation of an asset management system with Munisoft. On-Going
2. Explore and Initiate planning processes for recreation capital initiatives such as pool addition. Simultaneously, review the sustainability and funding strategy for recreation capital reserves. On-Going
3. Explore options and develop a plan for the concrete slab at the AGT Community Centre. Not Complete, 2021
4. Explore and develop a long-term plan for the urban orchard. Not Complete
5. Library continue to grow programming and promote as a community space (teen space, homework club, workshops) On hold due to COVID
6. Explore in house Tax Enforcement with Munisoft software. Not Complete

**Capital and Infrastructure**

1. Completion of the water meters and auto read project that was started in 2019. On-Going, 75% of the town is complete
2. Implement a scale at the landfill to ensure operational needs and efficiencies are achieved. On-Going, to be complete in summer 2021
3. Infrastructure, continue with the sewer lining project. On-Going
4. Paving Assessment Not Complete, due to COVID
5. Sidewalk grinding / cutting, to ensure community safety. Not Complete, due to COVID

**Serving the Community, Programming and Events**

1. Loraas Curbside garbage pick-up, starting January 2020.
2. Explore and implement further administrative efficiencies and service offerings (e-billing, on-line payments pre-authorized debiting for utilities, alternatives to stripe for on-line payments). On-Going
3. Continue to improve and update the website with the focus being on lots for sale and building permits. On-Going
4. Community-wide June event; Sports Day and Tradeshow. Not Complete, due to COVID
5. Explore the potential of a gymnastics program in Eston. Not Complete, due to COVID
6. Explore fundraising opportunities. Not Complete, due to COVID
7. Continue to promote and grow programming at the library (Summer programs, open to all, speakers) Not Complete, due to COVID

**Governance and Policy**

1. Continue reviewing and updating key bylaws and policies from all departments. On-Going

*Note that operations for the Health Care and Cemetery departments are overseen by the RM of Snipe Lake No. 259. For information on priorities for those departments, please contact the RM directly.*